Tool: Benefits Realisation Tracker

Track the real value of your digital transformation. The Made Smarter whitepaper highlights benefits such as cost savings, productivity gains, reduced downtime, improved quality, scalability, and workforce empowerment. This tracker helps you set baselines, measure progress, and ensure benefits are secure, inclusive, and sustainable (NWSmart5.0 addition).

This tracker helps manufacturing SMEs measure whether digital investments are delivering meaningful operational, workforce, cybersecurity, and sustainability improvements over time.

Recommended Review Cycle

- Establish realistic targets before implementation

- Measure progress consistently using the same metrics

- Involve operational teams as well as leadership

- Review cyber resilience and workforce impact alongside financial benefits

- Update the tracker quarterly to support continuous improvement

Template

Suggested KPI Examples

- Reduced downtime

- Faster production cycles

- Lower waste and energy use

- Improved staff engagement

- Reduced manual tasks

- Fewer cybersecurity incidents

- Better data visibility

| Benefit Area (from Made Smarter) | Expected Impact / Target | Baseline (Current) | Target Metric (e.g. %) | Actual at 3 months | Actual at 6 months | Actual at 12 months | Responsible Person | Cyber / Safe AI / EDI Check | Notes / Actions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Productivity & Efficiency (real-time data & automation) | e.g. 15–25% increase |  |  |  |  |  |  | Has cyber risk been assessed for new tools? |  |
| Cost Savings (predictive maintenance, reduced waste) | e.g. 10–20% reduction in downtime costs |  |  |  |  |  |  | Data privacy (GDPR) compliant? |  |
| Quality & Precision (consistency via digital tools) | e.g. defect rate reduced by 30% |  |  |  |  |  |  | Safe AI decision-making is explainable? |  |
| Workforce & Skills (tackling labour shortages, talent attraction) | e.g. 20% reduction in manual repetitive tasks; improved staff retention |  |  |  |  |  |  | EDI: Are diverse roles involved? Training accessible? |  |
| Sustainability & Resilience (net zero, scalability) | e.g. 15% lower energy use; better supply-chain visibility |  |  |  |  |  |  | Human-centric: Workers report higher job satisfaction? |  |
| Cyber Resilience & Risk Reduction (NWSmart5.0 priority) | Zero major incidents post-adoption |  |  |  |  |  |  | All new tech follows secure-by-design? |  |

Reminder:

All digital transformation activity should consider cybersecurity, safe AI practices, accessibility, inclusion, and workforce wellbeing.

Quarterly Reflection Questions

- Which improvements delivered the greatest value?

- Have any new cyber or AI risks emerged?

- Are employees confident using new technologies?

- What barriers are slowing progress?

- What should be prioritised next?

Disclaimer:

This tracker is intended as general guidance only and should not replace professional business, legal, financial, cybersecurity, or regulatory advice.

NWSmart5.0 Benefits Realisation Tracker – Adapted from Made Smarter Roadmap (2024)

Source: madesmarter-digital-transformation.pdf